## Gantt Chart
EMG-Controlled Robotic Hand & 7-DOF Robotic Arm — 30-Day Project Gantt Chart
Day-by-day schedule, Day 1–Day 30. All parts are pre-purchased and assumed to arrive by Day 7; Gray columns are scheduled rest days (2 every 7). Yellow cells are hard deadlines for a specific component.
Hand Subsystem
Arm Subsystem
Integration
Concept/Shared
Hard Deadline
Rest Day
ID | Task | Start Day | End Day | Duration (days) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1.1/2.1 | Requirements + kickoff (gesture set, joint layout, payload target) | 1 | 1 | 1 | bar: 1
2.3 | Arm: vision architecture decision | 1 | 1 | 1 | bar: 1
1.4 | Hand CAD: fingers, palm, tendon channels | 1 | 2 | 2 | bar: 1 to 2
1.5 | Hand CAD: forearm sleeve + wrist joint | 2 | 2 | 1 | bar: 2
2.4 | Arm CAD: base, 7 links, motor mounts, interface plate | 1 | 4 | 4 | bar: 1 to 4
2.4a | Cycloidal drive CAD: housing + disc (joints 1-3) | 3 | 4 | 2 | bar: 3 to 4
DL1 | HARD DEADLINE: Hand + Arm CAD files finalized, ready to print | 4 | 4 | 1 | bar: 4
1.6 | Print hand parts (fingers/palm) - first article | 3 | 4 | 2 | bar: 3 to 4
1.7 | Print hand parts - reprint pass if needed | 5 | 5 | 1 | bar: 5
2.5 | Print arm base + 3 proximal links | 4 | 5 | 2 | bar: 4 to 5
2.5a | Print cycloidal drive housings + discs (3 joints) | 5 | 5 | 1 | bar: 5
1.12pre | EMG firmware skeleton: acquisition + filtering (dev against simulated signal) | 1 | 3 | 3 | bar: 1 to 3
1.13pre | Gesture classification logic (dev against recorded/simulated EMG data) | 3 | 5 | 3 | bar: 3 to 5
2.11 | Forward/inverse kinematics solver (math only, no hardware needed) | 1 | 3 | 3 | bar: 1 to 3
2.12 | Trajectory/motion planning logic | 3 | 5 | 3 | bar: 3 to 5
2.16pre | Path planning algorithm dev (against simulated/sample scenes) | 4 | 5 | 2 | bar: 4 to 5
DL2 | HARD DEADLINE: All purchased parts received and inventoried | 8 | 8 | 1 | bar: 8
2.6 | Print remaining 4 distal links + end-effector plate | 8 | 8 | 1 | bar: 8
2.7 | Reprint pass: warped/failed structural & cycloidal parts | 9 | 9 | 1 | bar: 9
1.10 | Bench-test EMG sensor module (hardware now in hand) | 8 | 8 | 1 | bar: 8
1.8 | Hand mechanical assembly (tendons, bearings, pins) | 9 | 9 | 1 | bar: 9
1.9 | Mount servos in forearm housing | 10 | 10 | 1 | bar: 10
1.11 | Electrode placement + skin-contact validation | 10 | 10 | 1 | bar: 10
1.12 | EMG firmware: integrate with real sensor signal | 11 | 11 | 1 | bar: 11
2.9 | Wire 2x CNC shield/A4988 kits + power distribution | 9 | 10 | 2 | bar: 9 to 10
2.8 | Arm mechanical assembly incl. cycloidal stage install | 11 | 12 | 2 | bar: 11 to 12
2.10 | Motion controller firmware: homing, position control (real hardware) | 12 | 12 | 1 | bar: 12
DL3 | HARD DEADLINE: Hand fully assembled, Arm fully assembled | 12 | 12 | 1 | bar: 12
1.14 | EMG calibration routine + UI | 15 | 15 | 1 | bar: 15
1.15 | EMG recalibration iterations (electrode drift, cross-talk) | 15 | 16 | 2 | bar: 15 to 16
1.16 | Integrate classifier output -> servo mapping | 16 | 16 | 1 | bar: 16
1.17 | Grasp tuning (grip force, finger sequencing) | 17 | 18 | 2 | bar: 17 to 18
DL4 | HARD DEADLINE: Hand catches and holds ball standalone | 18 | 18 | 1 | bar: 18
2.13 | Camera calibration, workspace mapping | 15 | 15 | 1 | bar: 15
2.14 | Target (ball) detection via OpenCV/MediaPipe | 16 | 17 | 2 | bar: 16 to 17
2.15 | Obstacle detection + occupancy mapping | 17 | 17 | 1 | bar: 17
2.16 | Path planning algorithm with obstacle avoidance (real hardware) | 18 | 19 | 2 | bar: 18 to 19
2.18 | Integrate vision -> planner -> motion control loop | 18 | 19 | 2 | bar: 18 to 19
2.18a | Measure cycloidal joint torque vs bare gearbox | 19 | 19 | 1 | bar: 19
2.19 | Accuracy + obstacle avoidance tuning | 19 | 19 | 1 | bar: 19
DL5 | HARD DEADLINE: Arm reaches target + avoids obstacles standalone | 19 | 19 | 1 | bar: 19
3.1 | Mechanical integration: mount hand on arm | 22 | 22 | 1 | bar: 22
3.2 | Electrical integration: consolidate harness/power | 22 | 23 | 2 | bar: 22 to 23
3.3 | Software integration: unify control loop | 23 | 23 | 1 | bar: 23
DL6 | HARD DEADLINE: Combined hand+arm software pipeline runs end-to-end (no ball) | 23 | 23 | 1 | bar: 23
3.4 | End-to-end dry run (no ball) | 24 | 24 | 1 | bar: 24
3.5 | Integration debugging pass | 24 | 25 | 2 | bar: 24 to 25
DL7 | HARD DEADLINE: Integrated system ready for live-ball trials | 25 | 25 | 1 | bar: 25
3.7a | Live trials: full autonomous grasp-and-relocate (round 1) | 26 | 26 | 1 | bar: 26
3.7b | Live trials: full autonomous grasp-and-relocate (round 2) | 29 | 29 | 1 | bar: 29
3.8 | Rehearsal + contingency prep for final demo | 29 | 29 | 1 | bar: 29
DL8 | HARD DEADLINE: Final demonstration | 30 | 30 | 1 | bar: 30
3.10 | FINAL DEMONSTRATION | 30 | 30 | 1 | bar: 30

## BOM
EMG-Controlled Robotic Hand
Item | Qty | Cost | Total Cost | Purpose | Source | Progress
EMG Module | 1 | 18.87 | 18.87 | Muscle Contraction Detection | Amazon | Not Purchased
EMG Patches 100x | 1 | 17.05 | 17.05 | EMG Replacement Patches | Amazon | Not Purchased
MG90S Metal Gear 180 degree Micro Servo 8x | 1 | 18.99 | 18.99 | Finger Articulation Closed | Amazon | Not Purchased
Fishing Line | 1 | 0 | 0 | Finger Ligaments | Home | Not Purchased
Torsion Spring 10x | 1 | 5.72 | 5.72 | Finger Articulation Open | Amazon | Not Purchased
Screws, nuts, bolts, misc | 1 | 0 | 0 | Fixture and Assembly | Home | Not Purchased
PLA filament | 1 | 0 | 0 | Raw Material | Home | Not Purchased
uxcell 688ZZ Ball Bearing 8x16x5mm (20-pack) | 1 | 8.99 | 8.99 | Finger Joint Bearings | Amazon | Not Purchased
Hand Subtotal |  | 69.62
7-DOF Intelligent Robotic Arm
Item | Qty | Cost |  | Purpose | Source | Progress
FREENOVE Basic Starter Kit for ESP32-S3 | 2 | 25.56 | 51.12 | Microcontroller for Motor Control + Vision Interface | Amazon | Not Purchased
10Pack Nema 17 Stepper Motor | 1 | 66.14 | 66.14 | Arm Joint Actuation | Amazon | Not Purchased
ACEIRMC 3D Printer CNC Shield V3 + A4988 Driver | 2 | 9.99 | 19.98 | Motor Driver (1 packs = 5 drivers) | Amazon | Not Purchased
NICE-POWER DC Power Supply Variable 30V 10A | 1 | 44.99 | 44.99 | Driver/Motor Power Supply | Amazon | Not Purchased
HiLetgo KW12-3 Micro Limit Switch (10-Pack) | 1 | 7.99 | 7.99 | Joint Homing Reference (7 needed) | Amazon | Not Purchased
uxcell 10 Pcs 6807ZZ Deep Groove Ball Bearings, 35 x 47 x 7mm | 1 | 14.79 | 14.79 | Ball bearing output side | Amazon | Not Purchased
20Pcs 6703-ZZ Ball Bearing, 17x23x4mm | 1 | 14.94 | 14.94 | Ball bearing input side | Amazon | Not Purchased
uxcell 22mm Latching Emergency Stop Button (NC) | 1 | 8.99 | 8.99 | Manual Motor Power Cutoff | Amazon | Not Purchased
ELEGOO 120pc Dupont Jumper Wire Kit | 1 | 6.99 | 6.99 | ESP32 Prototyping + Sensor Wiring | Amazon | Not Purchased
Screws, nuts, bolts, misc | 1 | 0 | 0 | Fixture and Assembly | Home | Not Purchased
PLA filament | 1 | 0 | 0 | Raw Material | Home | Not Purchased
Zip Ties + Electrical Tape | 1 | 8 | 8 | Cable Management | Home Depot | Not Purchased
Arm Subtotal |  |  | 243.93
Grand Total |  |  | 243.93